## Sheet1
Issue ID | Issue Summary | Description | Link | Relevant Test Cases/ Code Line | Severity | Priority
1 | Bug | When the password is incorrect, the error message should indicate a wrong password, not a generic "WhiteLabelError." | http://localhost:8080/userloginvalidate | TID: 2 | Critical | High
2 | Bug | When the username is incorrect, the error message should indicate a wrong username, not a generic "WhiteLabelError." | http://localhost:8080/userloginvalidate | TID:3 | Critical | High
3 | Missing Feature | Description: Admin login should redirect to the admin page, not trigger a "validate page" error. | http://localhost:8080/ | TID: 7 | Catastrophic | Urgent
4 | Missing Feature | User login should redirect to the user Homepage, not a "validate page" | http://localhost:8080/userloginvalidate | TID 8 | Marginal | Medium
5 | Bug | Logging in with correct credentials should not trigger a "Whitelabel error." Issue added when there are multiple accounts with same username and password | http://localhost:8080/userloginvalidate | TID 17 | Marginal | Medium
6 | Bug | Attempting to register an existing user account should display an appropriate error message. | http://localhost:8080/register | TID: 10 | Marginal | Medium
7 | Bug | Attempting to register an existing admin account should display an appropriate error message. | http://localhost:8080/register | TID: 9 | Marginal | Medium
8 | Bug | Leaving the address empty during registration should display an error and not add the account to the database. | http://localhost:8080/register | TID: 14 | Critical | High
9 | Bug | The table name in the SELECT query should be corrected to match the schema | Line: 232 AdminController.java | Line 232 | Critical | High
10 | Bug | The table name in the UPDATE query should be corrected to match the schema | AdminController.java | Line 269 | Critical | High
11 | Bug | Clicking "add to cart" should add the item to the cart, not trigger a "Whitelabel Error Page." | On user/products | TID: 25 | Critical | High
12 | Bug | Clicking on the homepage should display the homepage, not trigger a "Whitelabel Error Page." | On user/products | TID: 26 | Critical | High
13 | Bug | Clicking on logout should show the login page, not trigger a "Whitelabel Error Page." | On user/products | TID: 27 | Critical | High
14 | Bug | Adding a product to the cart should redirect to "/user/products," not trigger a "Whitelabel Error Page." | On /carts | TID: 30 | Critical | High
15 | Bug | Clicking on the logo while logged in should display the homepage, not remain on the same page. | Clicks on logo | TID: 31 | Minor | Medium
16 | Missing Feature | Missing homepages for admin and user | N/A | N/A | Critical | High
17 | Missing Feature | Adding product functionality missing for both user and admin | N/A | N/A | Catastrophic | High
18 | Missing Feature | Admin control is missing. | N/A | N/A | Catastrophic | High
19 | Missing Feature | Separate login pages for both admin and user missing in standard mapping | N/A | N/A | Critical | High
20 | Missing Feature | The mapping of pages needs to be corrected according to the state diagram of the supposed system | N/A | N/A | Catastrophic | Urgent
21 | Missing Feature | The error page content and formatting need to be reviewed and edited as necessary. | N/A | N/A | Minor | Low
24 | Bug | Add Category By Admin Gives SQL Exception | https://localhost:8080/admin/categories | TID: 32 | Catastrophic | Urgent
25 | Bug | Delete Category By Admin Gives SQL Exception | https://localhost:8080/admin/categories. | TID: 33 | Catastrophic | Urgent
26 | Bug | Update Category By Admin while Passing Alpha-Numeric Values/ Special Character / Empty StringGives SQL Exception | https://localhost:8080/admin/categories. | TID: 35 | Marginal | Medium
27 | Bug | Add Product By Admin Gives SQL Exception | http://localhost:8080/admin/products | TID: 36 | Catastrophic | Urgent
28 | Bug | Delete Product By Admin Gives SQL Exception | http://localhost:8080/admin/products | TID: 37 | Catastrophic | Urgent
29 | Bug | Update Product By Admin Gives SQL Exception | http://localhost:8080/admin/products | TID: 38 | Catastrophic | Urgent
30 | Missing Feature | Delete Button Missing for Manage Customers | http://localhost:8080/admin/customers | NA | Critical | High
31 | Missing Feature | Update Product Post Mapping Logic Missing in Controller with un-used Request Param | AdminController.java | NA | Marginal | Medium
33 | Missing Feature | User Controller doesn't have API's for Buy and JSP pages doesn't even view the Buy at any point. | UserController.java | NA | Catastrophic | Urgent
34 | Missing Feature | Toast Messages for Succes and Error are missing | NA | NA | Minor | low
35 | Missing Feature | Incomplete Routes Mapping: States are not switching as per the required business need | All Controllers / Cart Page / Profile Page | NA | Catastrophic | Urgent
36 | Missing Feature